## Forecast listing 20230901
Infrastructure Services
Design and Construction Projects
Forecasted Tenders - September 2023 to March 2024 (Data: September 01, 2023)
Note: For information purposes only, dates are subject to change.
Project Code | Project Name | Project Type | Manager | Project Manager (to be hidden) | Project Authority (to be hidden) | Client Department | Project Template | Project Category | Project Phase Status | Forecasted Date | Tasks (To be hidden) | Client OBS
CR014689 | Stittsville Library Universal Washroom | Facilities | Knight, Matthew | Marcotte, Gabrielle | 201918.94 | Infrastructure & Water Services Dept. | Buildings and Grounds | Accessibility | Design | 2023-09-04 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000218 | St Laurent Ramps Remediation | Facilities | Knight, Matthew | Rattan, Supinderjit | 50000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Accessibility | Design | 2023-09-05 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch/Building & Park Asset Unit
CP000765 | Lemieux Island Intake Screen | Municipal | Kenny, Bruce | Ogilvie, Chris | 2755000 | Infrastructure & Water Services Dept. | Small Facilities | Plumbing | Implementation | 2023-09-05 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service
CF000496 | Hazeldean WWPS Generator Ph2 D&C | Facilities | Knight, Matthew | O'Brien, Christopher | 1700000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Sanitary Pumping Station Rehab | Design | 2023-09-08 | Tender Close | Infrastructure & Water Services Dept./Water Linear & Customer Services/Wastewater Collection Branch
CR014209 | Britannia Beach - Covered Lifeguards Stn | Facilities | Knight, Matthew | Rostami, Babak | 250000 | Rec, Cultural & Facility Services Dept. | Small Facilities | Site Furniture | Implementation | 2023-09-08 | Tender Close | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CR014620 | Crossing Bridge Jr Playstructure&Equip. | Facilities | Knight, Matthew | Veldkamp, Edward | 211000 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2023-09-08 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CR013977 | Dovercourt Parking & Stormwater Retrofi | Facilities | Knight, Matthew | Rostami, Babak | 209000 | Infrastructure & Water Services Dept. | Small Facilities | Parking Facility Renewal (Structures or Lots) | Design | 2023-09-12 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000166 | Bob MacQuarrie RCO Fire Alarm | Facilities | Knight, Matthew | Chakravorty, Nupur | 275000 | Infrastructure & Water Services Dept. | Small Facilities | Security Systems | Design | 2023-09-13 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CR013905 | RL Craine Park Design and Construction | Facilities | Knight, Matthew | Moran, Joanne | 420000 | Rec, Cultural & Facility Services Dept. | Parks | Grounds and Landscape | Implementation | 2023-09-14 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CR014848 | Nepean Sportsplex Repl Pool Scoreboard | Facilities | Knight, Matthew | Roberts, Darcy | 275000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Electrical | Design | 2023-09-14 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CP000834 | Woodroffe and Vanier Watermain Repair202 | Municipal | Kenny, Bruce | Reist, Christine | 500000 | Infrastructure & Water Services Dept. | Large Civil | Watermain | Design | 2023-09-15 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch/Watermain Rehabilitation Unit
CR014487 | Churchill Seniors Elevator Modernization | Facilities | Knight, Matthew | Marcotte, Gabrielle | 225000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Elevating / Lifting Devices | Design | 2023-09-15 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CR014651 | Ray Friel Pool Change Room Accessibility | Facilities | Knight, Matthew | Raizenne, Nick | 550000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Accessibility | Design | 2023-09-20 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000384 | Alcide Trudeau Park Asphalt Walkways | Facilities | Knight, Matthew | Smith, Tara | 138000 | Infrastructure & Water Services Dept. | Parks | Recreational Pathways | Design | 2023-09-22 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service
CP000772 | Ruisseau Park Ravine Rehabilitation | Municipal | Kenny, Bruce | Tremblay, Marc | 376000 | Infrastructure & Water Services Dept. | Large Civil | Storm Water Management | Design | 2023-09-22 | Tender Close | Infrastructure & Water Services Dept./Water Linear & Customer Services/Stormwater Management Branch
CF000270 | General Burns Resurface Parking Lot | Facilities | Knight, Matthew | Raizenne, Nick | 229000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Resurfacing | Design | 2023-09-25 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service
CP000845 | Expedited Access Road Installations | Municipal | Kenny, Bruce | Giamberardino, Nick | 600000 | Infrastructure & Water Services Dept. | Small Municipal | Gravel Road Upgrades | Planning | 2023-09-27 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service/Water Resources Planning & Eng Branch/Stormwater Management Branch
CP000110 | Carlington Heights Pumping Station Exp. | Facilities | Knight, Matthew | Smith, Kristin | 19292000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Water Pumping Station Rehab | Design | 2023-09-29 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CR014511 | Sunnyside Library Repair Stone Walls | Facilities | Knight, Matthew | Roberts, Darcy | 50000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Building Envelope | Design | 2023-09-29 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CR014801 | Ctrl Paterson - Repair Retaining Wall | Facilities | Knight, Matthew | Moran, Joanne | 80000 | Infrastructure & Water Services Dept. | Parks | Grounds and Landscape | Implementation | 2023-09-29 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CP000768 | Northside & Robertson WM Reconfiguration | Municipal | Kenny, Bruce | Arseneault, Andrew | 1316000 | Infrastructure & Water Services Dept. | Large Civil | Watermain | Design | 2023-10-01 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CR014697 | Springhurst Park - Dock Addition | Facilities | Knight, Matthew | Moran, Joanne | 132000 | Rec, Cultural & Facility Services Dept. | Parks | Public Boat Launch | Design | 2023-10-02 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CR014729 | Glebe CC Upgrade Preschool PlayStructure | Facilities | Knight, Matthew | Smith, Tara | 170000 | Rec, Cultural & Facility Services Dept. | Parks | Community Partnerships | Implementation | 2023-10-02 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000495 | CSO Flow Monitoring Project | Facilities | Knight, Matthew | Baird, David | 1439000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Plant Retro-fit / Upgrade | Design | 2023-10-04 | Tender Close | Infrastructure & Water Services Dept./Water Linear & Customer Services/Wastewater Collection Branch
CF000157 | Hickory St. ROW Streetscape Improvements | Facilities | Knight, Matthew | Pilgrim, Sandra | 643000 | Planning, Real Estate & Eco Dev. Dept. | Small Municipal | Streetscape | Design | 2023-10-05 | Tender Close | Planning, Real Estate & Eco Dev. Dept./ROW, Heritage & Urban Dsgn Services
CF000492 | Lemieux Wash Water Tank&Pump Room Rehab | Facilities | Knight, Matthew | Carneiro, Michael | 2030000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Plant Retro-fit / Upgrade | Design | 2023-10-06 | Tender Close | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Water Production - East Branch
CR014441 | Nepean Splx - Repl AHU 14/15&Condensers | Facilities | Knight, Matthew | Voelker, Kevin | 910000 | Infrastructure & Water Services Dept. | Buildings and Grounds | HVAC/Mechanical | Design | 2023-10-06 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000167 | Sandwell Green Fitness Equipment | Facilities | Knight, Matthew | Pelz, Heather | 188500 | Rec, Cultural & Facility Services Dept. | Parks | Site Furniture | Design | 2023-10-09 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000204 | Cattail Creek Park - Tennis Crt Renewal | Facilities | Knight, Matthew | Goettling, Jeff | 116000 | Rec, Cultural & Facility Services Dept. | Parks | Tennis Court | Implementation | 2023-10-10 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CR013525 | Brewer Park Office Bdg Demolish Facility | Facilities | Knight, Matthew | Voelker, Kevin | 851000 | Rec, Cultural & Facility Services Dept. | Buildings and Grounds | Demolition | Design | 2023-10-10 | Tender Close | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000220 | Beaverbrook CC Main Pool Heater Boiler | Facilities | Knight, Matthew | Rattan, Supinderjit | 65000 | Infrastructure & Water Services Dept. | Outdoor Recreation Areas | Building Envelope | Design | 2023-10-13 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch/Building & Park Asset Unit
CR014959 | Canterbury CC LED Lighting Retrofit | Facilities | Knight, Matthew | Rattan, Supinderjit | 176000 | Infrastructure & Water Services Dept. | Standing Offer | Lighting | Initiation | 2023-10-15 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch/Facilities Project Planning Unit
CR013939 | OC Blair Stn North Tower Elevators | Facilities | Knight, Matthew | Labelle, Shawn | 4050000 | Transit Services Dept. | Small Facilities | Elevating / Lifting Devices | Design | 2023-10-17 | Tender Close | Transit Services Dept./Transit Bus Oper & Maintenance Service
CP000117 | Ottawa South Pumping Station Upgrade | Municipal | Kenny, Bruce | Smith, Fraser | 18095000 | Community & Social Services Dept. | Complex Facility Renewal | Water Pumping Station Rehab | Design | 2023-10-20 | Tender Close | Community & Social Services Dept./Business Support Services
CP000724 | Connaught & Severn Sidewalk | Municipal | Kenny, Bruce | Mills, April | 300000 | Planning, Real Estate & Eco Dev. Dept. | Large Civil | Road | Design | 2023-10-20 | Tender Close | Planning, Real Estate & Eco Dev. Dept./Transportation Planning Service
CR013034 | Forster Farm - Replace Jr Playstructure | Facilities | Knight, Matthew | Munro, Brian | 240436.5 | Infrastructure & Water Services Dept. | Outdoor Recreation Areas | Play Structures | Design | 2023-10-20 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CR014814 | Osgoode CC & Arena - Rpl Roof Membrane | Facilities | Knight, Matthew | Roberts, Darcy | 197000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Large Roofing Projects | Implementation | 2023-10-20 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CR014419 | Kanata RC Arena Slab Replacement | Facilities | Knight, Matthew | Marcotte, Gabrielle | 1108000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Rink Slabs | Design | 2023-10-25 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000205 | Echo Park - Tennis Court & Fencing | Facilities | Knight, Matthew | Goettling, Jeff | 234000 | Rec, Cultural & Facility Services Dept. | Parks | Tennis Court | Design | 2023-10-30 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CR014384 | Erskine Johnston Evaporative Condenser | Facilities | Knight, Matthew | Raizenne, Nick | 368000 | Infrastructure & Water Services Dept. | Buildings and Grounds | HVAC/Mechanical | Design | 2023-11-02 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000199 | St. Paul’s Park- New Pathway Lighting | Facilities | Knight, Matthew | Moran, Joanne | 150000 | Rec, Cultural & Facility Services Dept. | Parks | Exterior Lighting | Implementation | 2023-11-03 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CP000749 | Niven's Wood Ditch Stabilization | Municipal | Kenny, Bruce | Wang, Bin | 150000 | Infrastructure & Water Services Dept. | Small Municipal | Slope Stabilization | Design | 2023-11-06 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CR013472 | Richelieu CC Exterior Painting | Facilities | Knight, Matthew | Roberts, Darcy | 47000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Building Envelope | Design | 2023-11-07 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000198 | Morgan's Grant Hydro Corridor - Dog Park | Facilities | Knight, Matthew | Goettling, Jeff | 243000 | Rec, Cultural & Facility Services Dept. | Parks | Grounds and Landscape | Design | 2023-11-08 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CP000682 | Bus Loop at Montreal Station | Municipal | Kenny, Bruce | Trudel, Justin | 4830000 | Planning, Real Estate & Eco Dev. Dept. | Large Civil | Transitway Rehabilitation | Design | 2023-11-09 | Tender Award | Planning, Real Estate & Eco Dev. Dept./Transportation Planning Service
CF000163 | ROPEC Phase 3 Guardrails & Platforms | Facilities | Knight, Matthew | Craig, Ian | 431000 | Infrastructure & Water Services Dept. | Small Facilities | Guards and Railings | Design | 2023-11-13 | Tender Close | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Wastewater Treatment Branch
CF000491 | RCAF & RCMP PS | Facilities | Knight, Matthew | Ouimet, Eric | 4752000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Sanitary Pumping Station Rehab | Design | 2023-11-17 | Tender Close | Infrastructure & Water Services Dept./Water Linear & Customer Services/Wastewater Collection Branch
CR014837 | Byward Garage Structural Concrete Repair | Facilities | Knight, Matthew | Labelle, Shawn | 631000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Parking Facility Renewal (Structures or Lots) | Design | 2023-11-17 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CR014585 | Fisher Elmdale Park -Gazebo Replacement | Facilities | Knight, Matthew | Moran, Joanne | 175000 | Infrastructure & Water Services Dept. | Parks | Gazebo / Amphitheatre | Design | 2023-11-20 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000216 | Alta Vista Library Universal Washroom | Facilities | Knight, Matthew | Roberts, Darcy | 50000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Accessibility | Design | 2023-11-21 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch/Building & Park Asset Unit
CF000210 | ROPEC Electrical Reliability | ROPEC | Hicks, Tyler | Courtland, Steven | 3000000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Plant Retro-fit / Upgrade | Design | 2023-11-23 | Tender Period | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Wastewater Treatment Branch
CF000487 | Insmill Park - Pathway Lighting (23) | Facilities | Knight, Matthew | Goettling, Jeff | 40000 | Infrastructure & Water Services Dept. | Parks | Exterior Lighting | Planning | 2023-11-27 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service
CP000540 | Winona, Wilmont & Elmgrove Integrated | Municipal | Kenny, Bruce | Pearce (Brown), Kim | 1008000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2023-11-29 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000801 | Bank St Canal Bridge – Arch #3 | Municipal | Kenny, Bruce | Smith, Fraser | 276000 | Infrastructure & Water Services Dept. | Large Civil | Bridge Renewal | Planning | 2023-11-30 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch/Transportation Assessment Unit
CR014619 | Mohawk Park - Sr Playstructure/Equipment | Facilities | Knight, Matthew | Moran, Joanne | 230000 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2023-11-30 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CR014641 | Bingham Park Improvements | Facilities | Knight, Matthew | Moran, Joanne | 2100000 | Rec, Cultural & Facility Services Dept. | Outdoor Recreation Areas | Grounds and Landscape | Design | 2023-11-30 | Tender Close | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000493 | Lemieux Relay Up&WPP Elect Co&Arc Flash | Facilities | Knight, Matthew | O'Brien, Christopher | 400000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Plant Retro-fit / Upgrade | Design | 2023-12-01 | Tender Close | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Water Production - East Branch
CP000534 | Road Sewer Renewal Pretoria Ave | Municipal | Kenny, Bruce | Lyons, Julie | 4674000 | Infrastructure & Water Services Dept. | Large Civil | Sanitary/Storm Sewer | Implementation | 2023-12-05 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000741 | Bilberry & Southmore Traffic Calming | Municipal | Kenny, Bruce | Pearce (Brown), Kim | 597000 | Planning, Real Estate & Eco Dev. Dept. | Small Municipal | Traffic Safety | Design | 2023-12-06 | Tender Period | Planning, Real Estate & Eco Dev. Dept./Transportation Planning Service
CP000558 | Smyth Road Cycling Safety Improvements | Municipal | Kenny, Bruce | Reist, Christine | 805000 | Transit Services Dept. | Large Civil | Cycling Routes | Design | 2023-12-15 | Tender Close | Transit Services Dept./Safety, Regulatory, Trng & Dev Service
CF000174 | Southcreek Village Park-Design&Construc | Facilities | Knight, Matthew | Veldkamp, Edward | 1214000 | Rec, Cultural & Facility Services Dept. | Parks | Play Structures | Design | 2023-12-18 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CR014669 | Dundonald Park New Spray Pad | Facilities | Knight, Matthew | Moran, Joanne | 470000 | Rec, Cultural & Facility Services Dept. | Parks | Splash Pads | Design | 2023-12-18 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000191 | Centrepointe Park New Accessible Swing | Facilities | Knight, Matthew | Veldkamp, Edward | 238000 | Rec, Cultural & Facility Services Dept. | Parks | Play Structures | Design | 2023-12-20 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CR014766 | Brewer Pool Repl Dehumid/Pool Filter Sys | Facilities | Knight, Matthew | Marcotte, Gabrielle | 855000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Pools | Design | 2023-12-21 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000483 | Ferguson Pratt - Asphalt Resurfacing | Facilities | Knight, Matthew | Pelz, Heather | 40000 | Infrastructure & Water Services Dept. | Parks | Recreational Pathways | Design | 2023-12-28 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch/Building & Park Asset Unit
CF000484 | Houlahan Park - Replace Playground | Facilities | Knight, Matthew | Pelz, Heather | 40000 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2023-12-28 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch/Building & Park Asset Unit
CF000518 | Kinsmen - Replace Kompan Structure | Facilities | Knight, Matthew | Moran, Joanne | 40000 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2023-12-28 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch/Building & Park Asset Unit
CF000170 | Heron Park Field House Renewal | Facilities | Knight, Matthew | Krahn, John | 1800000 | Rec, Cultural & Facility Services Dept. | New Buildings | Major Renovation | Planning | 2023-12-29 | Tender Close | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CP000693 | Carling Ave Retaining Walls | Municipal | Kenny, Bruce | Brazeau, Daniel | 143000 | Infrastructure & Water Services Dept. | Small Municipal | Retaining Walls | Design | 2023-12-29 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CR014810 | J.G. Mlacak Roof Areas 1-3 Replacement | Facilities | Knight, Matthew | Rostami, Babak | 1700000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Large Roofing Projects | Design | 2024-01-01 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CP000829 | Richmond West PS Reservoir Expansion | Municipal | Kenny, Bruce | DeLoyde, Jeff | 100000 | Infrastructure & Water Services Dept. | Small Facilities | Water Tanks | Design | 2024-01-02 | Tender Period | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Water Production West Branch
CF000131 | ICIP- CCR Parthia Park Jr Playstructure | Facilities | Knight, Matthew | Veldkamp, Edward | 222215 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2024-01-04 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CP000789 | Baseline Transit Priority Phase | Municipal | Kenny, Bruce | Ogilvie, Chris | 2058000 | Planning, Real Estate & Eco Dev. Dept. | Large Civil | Bus Rapid Transit (BRT) | Design | 2024-01-05 | Tender Close | Planning, Real Estate & Eco Dev. Dept./Transportation Planning Service
CR014639 | Woodroffe Park Field House | Facilities | Knight, Matthew | Voelker, Kevin | 316159 | Rec, Cultural & Facility Services Dept. | New Buildings | Large Buildings | Design | 2024-01-05 | Tender Close | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000130 | ICIP-CCR Silverbirch Park | Facilities | Knight, Matthew | Smith, Tara | 242537 | Rec, Cultural & Facility Services Dept. | Parks | Play Structures | Design | 2024-01-08 | Tender Period | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000133 | ICIP-CCR Munster Community Park | Facilities | Knight, Matthew | Veldkamp, Edward | 259443 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2024-01-08 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000499 | Meadowbreeze - Rplc Jr/Sr Structures | Facilities | Knight, Matthew | Pelz, Heather | 40000 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2024-01-08 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service
CF000510 | Isaie Savage - Replace Jr Play Structure | Facilities | Knight, Matthew | Pelz, Heather | 40000 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2024-01-08 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service
CR014696 | Greenboro Parks - Refresh Projects | Facilities | Knight, Matthew | Pelz, Heather | 450000 | Rec, Cultural & Facility Services Dept. | Outdoor Recreation Areas | Grounds and Landscape | Design | 2024-01-08 | Tender Period | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000179 | Lindenlea Comm Centre, Backyard Upgrade | Facilities | Knight, Matthew | Marcotte, Gabrielle | 25000 | Rec, Cultural & Facility Services Dept. | Buildings and Grounds | Community Partnerships | Design | 2024-01-09 | Tender Close | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CP000564 | Bank Street Widening & Reconstruction | Municipal | Kenny, Bruce | Gallagher, Stephen | 18584000 | Planning, Real Estate & Eco Dev. Dept. | Large Civil | New Road | Design | 2024-01-12 | Tender Close | Planning, Real Estate & Eco Dev. Dept.
CR013084 | St Laurent - Replace Chiller System | Facilities | Knight, Matthew | Voelker, Kevin | 188000 | Infrastructure & Water Services Dept. | Buildings and Grounds | HVAC/Mechanical | Design | 2024-01-12 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000519 | Roy Park - Replace Splash Pad | Facilities | Knight, Matthew | Smith, Tara | 40000 | Infrastructure & Water Services Dept. | Parks | Splash Pads | Design | 2024-01-15 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch/Building & Park Asset Unit
CR013772 | ROPEC Aeration Blower Expansion | Facilities | Knight, Matthew | Matuszewski, Kris | 5691000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Plant Retro-fit / Upgrade | Design | 2024-01-15 | Tender Period | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Wastewater Treatment Branch
CR014832 | Brian Kilrea Arena Heating Boilers | Facilities | Knight, Matthew | Marcotte, Gabrielle | 161000 | Infrastructure & Water Services Dept. | Buildings and Grounds | HVAC/Mechanical | Implementation | 2024-01-17 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000153 | ICIP-Walter Baker Park - splash pad exp | Facilities | Knight, Matthew | Smith, Tara | 515000 | Rec, Cultural & Facility Services Dept. | Parks | Splash Pads | Design | 2024-01-18 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000526 | Kars Rink Upgrade Project | Facilities | Knight, Matthew | Veldkamp, Edward | 148000 | Rec, Cultural & Facility Services Dept. | Parks | Outdoor Rink | Planning | 2024-01-18 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000498 | Lemieux Basin 4 & 5 Gates Rehabilitation | Facilities | Knight, Matthew | Baird, David | 1200000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Plant Retro-fit / Upgrade | Design | 2024-01-19 | Tender Close | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Water Production - East Branch
CP000667 | Bank Street Stormwater Soil Cell Pilot | Municipal | Kenny, Bruce | Stoddard, Steven | 676000 | Public Works Dept. | Large Civil | Storm Water Management | Design | 2024-01-23 | Tender Close | Public Works Dept./Parks Maintenance & Forestry Services
CP000619 | 2021 RSAP Intersection Modifications | Municipal | Kenny, Bruce | Rathwell, Stacey | 400000 | Transit Services Dept. | Large Civil | Intersection Modification | Design | 2024-01-25 | Tender Close | Transit Services Dept./Safety, Regulatory, Trng & Dev Service
CF000521 | Fisher Heights - Replace Playground | Facilities | Knight, Matthew | Veldkamp, Edward | 40000 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2024-01-26 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service
CF000307 | Kanata Leisure Pool Repaint Roof Trusses | Facilities | Knight, Matthew | Roberts, Darcy | 127000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Painting (Structural Elements) | Initiation | 2024-01-29 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service
CP000649 | Leitrim Pumping Station Upgrade | Facilities | Knight, Matthew | El-Sarji, Mohamed | 619000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Sanitary Pumping Station Rehab | Design | 2024-01-29 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000500 | Pineglen Park - Replace Playground | Facilities | Knight, Matthew | Veldkamp, Edward | 40000 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2024-01-30 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service
CP000419 | Integrated: Canterbury Arch Plesser | Municipal | Kenny, Bruce | Alchawa, Houssam | 1142000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-01-31 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000524 | 2020 MUP Renewal East & West | Municipal | Kenny, Bruce | Pulsifer, Andrew | 300000 | Infrastructure & Water Services Dept. | Road Rehabilitation | Multi-use Pathway | Design | 2024-01-31 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000124 | Hurdman B. Water Pumping Ss. Upgrades | Facilities | Knight, Matthew | de Laat, Jeff | 27786216.47 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Water Pumping Station Rehab | Design | 2024-02-02 | Tender Close | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Water Production - East Branch
CP000696 | Integrated Renewal - Glebe Ave | Municipal | Kenny, Bruce | DeLoyde, Jeff | 500000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-02-05 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CF000508 | Lemieux & Britannia MCC Replacement | Facilities | Knight, Matthew | Hayes, Pamela | 2000000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Plant Retro-fit / Upgrade | Planning | 2024-02-08 | Tender Close | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Water Production - East Branch
CR014492 | Pinhey's Point - Exter. Walls Repointing | Facilities | Knight, Matthew | Raizenne, Nick | 111000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Building Envelope | Design | 2024-02-09 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CP000822 | Hazeldean A2 Local watermain | Municipal | Kenny, Bruce | Stoddard, Steven | 400000 | Infrastructure & Water Services Dept. | Large Civil | Watermain | Design | 2024-02-12 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch/Watermain Rehabilitation Unit
CP000823 | 2023 Sidewalk and Pathway | Municipal | Kenny, Bruce | Giamberardino, Nick | 313000 | Infrastructure & Water Services Dept. | Small Municipal | Sidewalks | Initiation | 2024-02-12 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch/Transportation Assessment Unit/Road Rehabilitation Sect.
CF000200 | Gregory-Casey Dog Park - New Park Devp | Facilities | Knight, Matthew | Veldkamp, Edward | 375000 | Rec, Cultural & Facility Services Dept. | Parks | Grounds and Landscape | Design | 2024-02-13 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CF000541 | Trail Waste Facility Stge 3B Final Cover | Facilities | Knight, Matthew | Beauregard, Marc | 0 | Public Works Dept. | Large Civil | Landfill | Initiation | 2024-02-13 | Tender Period | Public Works Dept./Solid Waste Services
CF000212 | Jock River Park (North) | Facilities | Knight, Matthew | Veldkamp, Edward | 3800000 | Rec, Cultural & Facility Services Dept. | Parks | Grounds and Landscape | Design | 2024-02-15 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CP000548 | Longpre Lebrun Marquette Integrated | Municipal | Kenny, Bruce | Lacasse, Frederic | 2450000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-02-16 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CR013966 | Alexander Park CC Roof/Roof Deck | Facilities | Knight, Matthew | Roberts, Darcy | 476000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Large Roofing Projects | Design | 2024-02-20 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CP000713 | Renewal Airport Parkway Overpass | Municipal | Kenny, Bruce | Lolli, Joseph | 440000 | Infrastructure & Water Services Dept. | Large Civil | Bridge Renewal | Design | 2024-02-21 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000757 | Shadow Ridge Production Well Phase 2 | Municipal | Kenny, Bruce | DeLoyde, Jeff | 0 | Infrastructure & Water Services Dept. | Small Facilities | Expansion | Design | 2024-02-22 | Tender Close | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Water Production - East Branch
CF000213 | Andy Shields Fenced Off-Leash Dog Park | Facilities | Knight, Matthew | Goettling, Jeff | 203000 | Rec, Cultural & Facility Services Dept. | Parks | Fitness Trail | Design | 2024-02-26 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CP000787 | St. Laurent Blvd Fibre Network Install | Municipal | Kenny, Bruce | Giamberardino, Nick | 0 | Public Works Dept. | Large Civil | Traffic Signals | Initiation | 2024-02-26 | Tender Period | Public Works Dept./Traffic Services
CP000790 | Westbury Fellows Drury Parkway Sidewalks | Municipal | Kenny, Bruce | Gomez-Gonzalez, Francisco | 1234000 | Planning, Real Estate & Eco Dev. Dept. | Small Municipal | Sidewalks | Planning | 2024-02-28 | Tender Period | Planning, Real Estate & Eco Dev. Dept./Transportation Planning Service
CF000201 | Dutchie’s Hole Park - Dock Addition | Facilities | Knight, Matthew | Moran, Joanne | 144000 | Rec, Cultural & Facility Services Dept. | Parks | Grounds and Landscape | Design | 2024-02-29 | Tender Award | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CP000825 | Laurier Ave Percy St Traffic Control | Municipal | Kenny, Bruce | Delaney, Kyle | 0 | Public Works Dept. | Large Civil | Traffic Safety | Design | 2024-02-29 | Tender Close | Public Works Dept./Traffic Services
CF000532 | Stonecrop Park – Ph 1 (Quinn Farm) CBP | Facilities | Knight, Matthew | Moran, Joanne | 1204000 | Rec, Cultural & Facility Services Dept. | Parks | Play Structures | Planning | 2024-03-01 | Tender Period | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CP000848 | Carp Road Culvert Extension | Municipal | Kenny, Bruce | Pearce (Brown), Kim | 120000 | Infrastructure & Water Services Dept. | Small Municipal | Slope Stabilization | Planning | 2024-03-01 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch/Transportation Assessment Unit/Structures Programs Sect.
CR014803 | Jim Durrell RC Link & Lobby Roof Repl | Facilities | Knight, Matthew | Rattan, Supinderjit | 270000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Large Roofing Projects | Design | 2024-03-01 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000515 | Clarence Maheral - Pathway Lighting | Facilities | Knight, Matthew | Labelle, Shawn | 40000 | Infrastructure & Water Services Dept. | Parks | Exterior Lighting | Initiation | 2024-03-04 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service
CP000778 | MacFarlane/White Adler/Naskapi/Albion | Municipal | Kenny, Bruce | Porter, James | 1518000 | Planning, Real Estate & Eco Dev. Dept. | Large Civil | Area Traffic Management Measures | Design | 2024-03-06 | Tender Close | Planning, Real Estate & Eco Dev. Dept./Transportation Planning Service
CP000655 | Integrated Renewal Summit Avenue | Municipal | Kenny, Bruce | Arseneault, Andrew | 915000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-03-08 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000308 | Bank Street Integrated | Municipal | Kenny, Bruce | Tubb, Roxanne | 8341000 | Infrastructure & Water Services Dept. | Large Civil | Coordinated Sewer & Water | Design | 2024-03-12 | Tender Close (Phase 1) | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000809 | 2022/2023 PAIR Project and SLoAT | Municipal | Kenny, Bruce | Porter, James | 440000 | Public Works Dept. | Small Municipal | Sidewalks | Design | 2024-03-14 | Tender Close | Public Works Dept./Traffic Services
CP000763 | McArthur at Lafontaine Modifications | Municipal | Kenny, Bruce | Gomez-Gonzalez, Francisco | 302878 | Infrastructure & Water Services Dept. | Large Civil | Intersection Modification | Design | 2024-03-15 | Tender Close | Infrastructure & Water Services Dept./Infrastructure Services
CP000805 | Intersect Improve Spratt/Earl Armstrong | Municipal | Kenny, Bruce | Lolli, Joseph | 205000 | Public Works Dept. | Small Municipal | Traffic Safety | Design | 2024-03-15 | Tender Close | Public Works Dept./Traffic Services
CF000328 | Nepean Sportsplex Ph 2 Main Switchboard | Facilities | Knight, Matthew | Raizenne, Nick | 131000 | Infrastructure & Water Services Dept. | Buildings and Grounds | Electrical | Design | 2024-03-18 | Tender Period | Infrastructure & Water Services Dept./Asset Management Service
CF000215 | Brian Kilrea Arena Changerooms Upgrade | Facilities | Knight, Matthew | Marcotte, Gabrielle | 50000 |  | Buildings and Grounds | Accessibility | Planning | 2024-03-22 | Tender Close
CF000481 | Terry Fox Athletic Fac - Power Upgrade | Facilities | Knight, Matthew | Marcotte, Gabrielle | 500000 | Rec, Cultural & Facility Services Dept. | Buildings and Grounds | Electrical | Planning | 2024-03-22 | Tender Close | Rec, Cultural & Facility Services Dept./Parks & Facilities Planning Services
CP000748 | Integrated Renewal: Highland Avenue | Municipal | Kenny, Bruce | Delaney, Kyle | 650000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-03-26 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000423 | Integrated:Carling Churchill Kirkwood | Municipal | Kenny, Bruce | Lyons, Julie | 2900000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-03-27 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000725 | Integrated Renewal - Oakhill | Municipal | Kenny, Bruce | DeLoyde, Jeff | 586000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-03-28 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CF000129 | ICIP-CCR McNabb Park | Facilities | Knight, Matthew | Moran, Joanne | 193026 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2024-03-29 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000132 | ICIP-CCR Hemlock Park | Facilities | Knight, Matthew | Moran, Joanne | 180950 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2024-03-29 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service/Facilities Asset Management Branch
CF000494 | Lemieux MCC3M and Motor Replacements | Facilities | Knight, Matthew | Carneiro, Michael | 790000 | Infrastructure & Water Services Dept. | Complex Facility Renewal | Plant Retro-fit / Upgrade | Design | 2024-03-29 | Tender Close | Infrastructure & Water Services Dept./Water Facilities & Treatment Services/Water Production - East Branch
CF000522 | Frank J Licari - Replace Play Equipment | Facilities | Knight, Matthew | Moran, Joanne | 40000 | Infrastructure & Water Services Dept. | Parks | Play Structures | Design | 2024-03-29 | Tender Award | Infrastructure & Water Services Dept./Asset Management Service
CP000643 | Laurier Ave Cycling Modifications | Municipal | Kenny, Bruce | Arseneault, Andrew | 450000 | Transit Services Dept. | Large Civil | Cycling Routes | Design | 2024-03-29 | Tender Close | Transit Services Dept./Safety, Regulatory, Trng & Dev Service
CP000665 | Integrated Renewal - Drouin Avenue | Municipal | Kenny, Bruce | Mojsej, Joe | 684000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-03-29 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000747 | Integrated Renewal Ella and Ralph St | Municipal | Kenny, Bruce | Trudel, Justin | 1050000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-03-29 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch
CP000654 | Integrated: James St and Kent St | Municipal | Kenny, Bruce | Mojsej, Joe | 1920000 | Infrastructure & Water Services Dept. | Large Civil | Integrated Road | Design | 2024-03-31 | Tender Close | Infrastructure & Water Services Dept./Asset Management Service/Linear Asset Management Branch